## Sheet1
RNFA DIAG Action Plan: dated 21/05/2024
RAG | Activity | Responsible | Date
FIRST STEPS
| Review and agree Terms of Reference | WO Miller-McCaffrey | 2024-05-21
| Review and agree DIAG Priorities | WO Miller-McCaffrey | 2024-05-21
| Review and agree DIAG Code of Conduct | WO Miller-McCaffrey | 2024-05-21
IAG biogs - role/organisation and EDI interests
Agree annual meetings
| What is success? - For RNFA -For RNFA IAG | Code of Governance compliance
What is inclusion?
| Surveys (staff / coaches / players / referees) | see D&I questionnaire 14/10/24 | 2024-10-14
Milestones
| Review Comms plan - Internal -External | to be agreed at next DIAG after baseline survey Q4 2024
Core Values and Sport
CURRENT
| Statistic Gathering - Registered Male/Female/Disabled players - Registered Male/Female/Disabled Referees - Registered Male/Female/Disabled Coaches | see RNFA D&I questionnaire 14/10/24 | 2024-10-29
| Internal EDI audit (staff / committee / IAG / players / referees / coaches) | see RNFA D&I questionnaire 14/10/24 | 2024-10-29
Review Recruitment Policy
Review Induction Policy
Review website language and imagery
Review Hall of Fame and selection criteria (Players, Staff, Coaches, Refs)
Review List of VPs and selection criteria
Review reporting process for abuse / discrimination / poor behaviour
Introduce inclusion awareness sessions - staff / board / players / coaches / refs
| Barriers to involvement | RN wide sport survey due Q3/4 2024
| Gaps for volunteering | to be agreed at next DIAG after baseline survey Q4 2024
Reward & Recognition - so far
| Gaps for participation | to be agreed at next DIAG after baseline survey Q4 2024
FUTURE
Collaborate with ERG's
Youth Team Forum
Innovation
| My Navy App Data Gathering | RN wide sport survey due Q3/4 2024
| Targeted measures to reduce inequality to be agreed after discssion of RNFA baseline D&I survey results | to be agreed at next DIAG after baseline survey Q4 2024
| Events | Football Development Manager